## Detail FunctionList (VN)
26.5
[5 empty] | Normal Productivity |  |  | 5.4 | 5.4 | 5.4 |  | Normal Productivity : using for "New function"; Kaizen Productivity : using for "Modified function" and "BCT testing function".
[5 empty] | Kaizen Productivity |  |  | 5.7 | 5.9 | 5.9 | [40 empty] | Standard Dev Days
|  |  | Function | Summary of Function | Kaizen Function Type | FunctionID | Priority | Screen | Batch | Report | Remark | Standard Effort |  |  |  | FunctionPoint |  |  |  |  | Screen | [11 empty] | Report |  |  |  |  | Batch | [12 empty] | DR | DN&PU | IFT/BCT
[21 empty] | Mater/Transaction | [9 empty] | Linked Table/Transaction |  | Report |  |  |  |  | Upload (gửi đi) | [5 empty] | Download (lấy về) | [5 empty] | Calculation/Data Edit
[12 empty] | Standard MM | Complexity | Similarity | MM | FP | Complexity | Similarity | Final FP | MM | Basic for Retrieve | Basic for Update | Incremental Target Tables (retrieve) | Incremental Target Tables (update) | Combobox accessing Table | Display Sub-Screen | Refer/Check Master | Check Input Items | Additional Functions (On Client) | Additional Functions (Server Access) | Basic | Additional | Basic | Incremental Target Tables | Incremental Forms | Special Edit | Special Layout | Basic | Incremental target tables | Refer/Check Master | Data convert and edit | Communicate with other system | Additional function | Basic | Incremental target tables | Refer/Check Master | Data convert and edit | Communicate with other system | Additional function |  | 30% | 40% | 30%
| 1 |  | Master Data | Description | [6 empty] | Phase 1
|  | 1.01 | Setup account for PIC Dept/PIC Div | Chức năng dùng để tạo tài khoản cho người phụ trách Budget của Dept/ Group | New Function | F_1.01 | M | 1 |  |  |  | 0.7 |  |  | 0.7 | 2 |  |  | 2 | 0.37037 | 1 | 1 | [28 empty] | 2.2222 | 2.963 | 2.2222
|  | 1.02 | Open/Close Mid-term Period (FY24-FY28) | Trong lúc đang chạy Short-term thì phòng ban cần phải làm plan của Mid-term nữa, chức năng này cho phép mở/ đóng song song khi đang dùng Short term | New Function | F_1.02 | M | 1 |  |  |  | 0.7 |  |  | 0.7 | 6.5 |  |  | 6.5 | 1.2037 | 1 | 1 | 3 | 3 | 2 | 5 | 3 | [23 empty] | 7.2222 | 9.6296 | 7.2222
|  | 1.03 | Open/Close Quarterly (Original- 3Q) | Chức năng mở/ đóng plan hàng Quý tại năm tài chính đó (ví dụ: Đang là FY23 thì cần làm plan Quarterly cho 1st cut, financial plan, 1Q, 2Q, 3Q) | New Function | F_1.03 | M | 1 |  |  |  | 0.7 |  |  | 0.7 | 6.2 |  |  | 6.2 | 1.1481 | 1 | 1 | 4 | 4 | 5 | 1 | 2 |  |  |  | 1 | [19 empty] | 6.8889 | 9.1852 | 6.8889
|  | 1.04 | Setup segment 1 | Dùng đề định nghĩa theo loại chi phí - Cost type | New Function | F_1.04 | M | 1 |  |  |  | 0.7 |  |  | 0.7 | 2.6 |  |  | 2.6 | 0.48148 | 1 | 1 | 1 | 1 | 1 | [25 empty] | 2.8889 | 3.8519 | 2.8889
|  | 1.05 | Setup segment 2 | Dùng để tạo Segment 2, được gắn liền với từng hoạt động, dự án riêng - Project code | New Function | F_1.05 | M | 1 |  |  |  | 0.7 |  |  | 0.7 | 6.4 |  |  | 6.4 | 1.1852 | 1 | 1 |  | 5 | 8 | 3 | 5 | 1 | [22 empty] | 7.1111 | 9.4815 | 7.1111
|  | 1.06 | Setup segment 3 | Dùng để tạo Segment 3 được gán với từng phòng ban cụ thể - Budget owner | New Function | F_1.06 | M | 1 |  |  |  | 0.7 |  |  | 0.7 | 5 |  |  | 5 | 0.92593 | 1 | 1 |  | 3 | 3 | 3 | 3 | [23 empty] | 5.5556 | 7.4074 | 5.5556
|  | 1.07 | Setup segment 4 | Dùng để tạo Segment 4 ghi nhận cho Loại tài sản - Asset Class và GL account level 4 | New Function | F_1.07 | M | 1 |  |  |  | 0.7 |  |  | 0.7 | 2.3 |  |  | 2.3 | 0.42593 | 1 | 1 |  | 1 | [26 empty] | 2.5556 | 3.4074 | 2.5556
|  | 1.08 | Setup segment 5 | Dùng để tạo Seg5, ghi nhận cho Asset Items và GL account level 5 & Activities | New Function | F_1.08 | M | 1 |  |  |  | 0.7 |  |  | 0.7 | 2.4 |  |  | 2.4 | 0.44444 | 1 | 1 |  | 1 |  |  |  | 2 | [22 empty] | 2.6667 | 3.5556 | 2.6667
|  | 1.09 | Setup project code (combine seg1 + seg2) | Dùng để tạo Project code: gồm Seg1 +seg2 được ngăn cách bởi dấu chấm "." | New Function | F_1.09 | M | 1 |  |  |  | 0.7 |  |  | 0.7 | 3.1 |  |  | 3.1 | 0.57407 | 1 | 1 |  | 2 |  | 1 | [24 empty] | 3.4444 | 4.5926 | 3.4444
|  | 1.1 | Full WBS (combine 1-5) | Hoàn thiện 1 dải code full trên hệ thống cần đầu đủ 5 segment kia gộp lại, tổng có 24 ký tự | [6 empty] | Phase 1
|  | 1.11 | Ex. rate: Planning (by quarterly) | Tỷ giá được áp dụng tại mỗi quý khi làm planning
| 2 |  | Quản lý budget | [7 empty] | Phase 1
|  | 2.01 | Mid-term budget plan | Chức năng quản lý số liệu của Mid-term lên hệ thống theo năm (thường là 5 năm) Có luồng duyệt/ từ chối dữ liệu giữa các cấp | New Function | F_2.01 | M | 1 |  |  |  | 0.7 |  |  | 0.7 | 8.9 |  |  | 8.9 | 1.6481 | 1 | 1 | 5 | 5 |  | 3 | 3 | 2 | 3 | 1 | [20 empty] | 9.8889 | 13.1852 | 9.8889
|  | 2.02 | Submission status report (Mid-term) | Đẩy lại số liệu về hệ thống S/4 của Vùng và báo lại cho mình biết đã đẩy thành công hết hay chưa | New Function | F_2.02 | M | 1 |  |  |  | 0.7 |  |  | 0.7 | 10.4 |  |  | 10.4 | 1.9259 | 1 | 1 | 1 | 1 |  | 7 | 3 | 3 | 4 | 2 | [20 empty] | 11.5556 | 15.4074 | 11.5556
|  | 2.03 | Short term budget plan | Chức năng quản lý số liệu hàng quý lên hệ thống theo tháng (thường phải làm 5 quý trong 1 năm tài chính FY) Có luồng duyệt/ từ chối dữ liệu giữa các cấp | New Function | F_2.03 | M | 1 |  |  |  | 0.7 |  |  | 0.7 | 10.4 |  |  | 10.4 | 1.9259 | 1 | 1 | 5 | 5 |  | 1 | 3 | 1 | 2 | 4 | [20 empty] | 11.5556 | 15.4074 | 11.5556
|  | 2.04 | Submission status report (Short-term) | Đẩy lại số liệu về hệ thống S/4 của Vùng và báo lại cho mình biết đã đẩy thành công hết hay chưa | New Function | F_2.04 | M |  | 1 |  |  | 0.65 |  |  | 0.65 | 9.2 |  |  | 9.2 | 1.7037 | [17 empty] | 1 |  | 1 | 3 | 1 | 5 | 1 | [5 empty] | 1 | 10.2222 | 13.6296 | 10.2222
|  | 2.05 | BG adjustment (Budget release/Transfer/Add on budget) | Chức năng cho phòng ban thao tác chuyển tiền từ code A sang code B để đảm bảo không bị âm, hoặc thêm mới hẳn 1 khoản budget do xin được tiền từ TOP approval, hoặc những khoản proposal đã được báo và phê duyệt từ TOP) | New Function | F_2.05 | M | 1 |  |  |  | 0.7 |  |  | 0.7 | 4 |  |  | 4 | 0.74074 | 1 | 1 | 2 | 2 | [5 empty] | 1 | [20 empty] | 4.4444 | 5.9259 | 4.4444
|  | 2.06 | Consumption (Commitment + Actual) | Chi tiêu của phòng ban + Actual + Commitment, Actual là những khoản đã có invoice về và được kế toán booking, Commitment là các khoản mới làm PR/PO/Proposal/Ringi đang được triển khai làm chứ chưa finish, chưa có invoice về | New Function | F_2.06 | M |  | 1 |  |  | 0.65 |  |  | 0.65 | 1 |  |  | 1 | 0.18519 | [17 empty] | 1 | [12 empty] | 1.1111 | 1.4815 | 1.1111
|  | 2.07 | Latest plan (including: BF plan + budget adj) | Latest plan = Plan tại quý đó + khoản thêm/bớt trong quý mà họ phân bổ | New Function | F_2.07 | M |  |  | 1 |  | 0.5 |  |  | 0.5 | 2.5 |  |  | 2.5 | 0.46296 | [12 empty] | 1 |  |  |  | 3 | [13 empty] | 2.7778 | 3.7037 | 2.7778
|  | 2.08 | Mail consumption monthly | Gửi mail thông báo về chi tiêu hàng tháng cho tất cả phòng ban của cty, để PIC nắm được và check lại chi tiêu phòng mình
|  | 2.09 | Budget Warning (Daily send by email) | Mail cảnh báo hàng ngày với những code bị âm để user nắm được và làm transfer/add on thêm tiền ở những code cần điều chỉnh này | New Function | F_2.09 | M |  |  | 1 |  | 0.5 |  |  | 0.5 | 2.5 |  |  | 2.5 | 0.46296 | [12 empty] | 1 |  |  |  | 3 | [13 empty] | 2.7778 | 3.7037 | 2.7778
| 3 |  | Report | [7 empty] | Phase 1
|  | 3.01 | KPIs report (Monthly) | Tính toán, lọc tách số liệu để lên 1 bảng tổng quan báo TOP | New Function | F_3.01 | M | 1 |  |  |  | 0.7 |  |  | 0.7 | 4.3 |  |  | 4.3 | 0.7963 | 1 | 2 | 2 | 3 | [26 empty] | 4.7778 | 6.3704 | 4.7778
|  | 3.02 | Depreciation Report | Tính toán dữ liệu để lên số khấu hao cho từng Car model theo năm | New Function | F_3.02 | M |  |  | 1 |  | 0.5 |  |  | 0.5 | 2.9 |  |  | 2.9 | 0.53704 | [12 empty] | 1 | 2 | 1 |  | 1 | [13 empty] | 3.2222 | 4.2963 | 3.2222
|  | 3.03 | Calculator CR remain by Div (Regular/Project) | Tính toán các khoản Cost reduce remain mà phòng ban cắt giảm được theo Category: Regular/Prj
|  | 3.04 | Labor Cost Report | Báo cáo cho Labor cost
|  | 3.05 | Fixed cost catagory/historical | Theo template của vùng, hệ thống sẽ chạy dữ liệu vào các trường quy định | New Function | F_3.05 | M |  |  | 1 |  | 0.5 |  |  | 0.5 | 2.9 |  |  | 2.9 | 0.53704 | [12 empty] | 1 | 2 | 1 |  | 1 | [13 empty] | 3.2222 | 4.2963 | 3.2222
|  | 3.06 | PP06 | Theo template của vùng, hệ thống sẽ chạy dữ liệu vào các trường quy định | New Function | F_3.06 | M | 1 |  |  |  | 0.7 |  |  | 0.7 | 9.1 |  |  | 9.1 | 1.6852 | 1 | 1 | 4 | 4 |  |  |  | 1 | 4 | 3 | [20 empty] | 10.1111 | 13.4815 | 10.1111
|  | 3.07 | PP02 | Theo template của vùng, hệ thống sẽ chạy dữ liệu vào các trường quy định | New Function | F_3.07 | M |  |  | 1 |  | 0.5 |  |  | 0.5 | 2.9 |  |  | 2.9 | 0.53704 | [12 empty] | 1 | 2 | 1 |  | 1 | [13 empty] | 3.2222 | 4.2963 | 3.2222
|  | 3.08 | Cashflow report (Calculation/Report) | Tính toán plan để forecast cashflow hàng tháng | New Function | F_3.08 | M | 1 |  |  |  | 0.7 |  |  | 0.7 | 9.1 |  |  | 9.1 | 1.6852 | 1 | 1 | 4 | 4 |  |  |  | 1 | 4 | 3 | [20 empty] | 10.1111 | 13.4815 | 10.1111
| 4 |  | Tích hợp In/ Out hệ thống khác | [7 empty] | Phase 1
|  | 4.01 | Đồng bộ thông tin từ hệ thống nhân sự | Lấy dữ liệu để lên được: Labor cost Report | New Function | F_4.01 | M |  | 1 |  |  | 0.65 |  |  | 0.65 | 3.5 |  |  | 3.5 | 0.64815 | [17 empty] | 1 | 1 |  |  | 1 |  |  |  | 1 | 3 | 1 |  |  | 3.8889 | 5.1852 | 3.8889
|  | 4.02 | Đồng bộ thông tin từ hệ thống PRC, INVENTORY, BTS, DIRECT AP,… | Lấy dữ liệu để biết được Consumption của phòng ban (Actual + Commitment) | New Function | F_4.02 | M |  | 1 |  |  | 0.65 |  |  | 0.65 | 3.5 |  |  | 3.5 | 0.64815 | [17 empty] | 1 | 1 |  |  | 1 |  |  |  | 1 | 1 | 1 |  |  | 3.8889 | 5.1852 | 3.8889
|  | 4.03 | Đồng bộ WBS sang hệ thông S4 | Đẩy thông tin dữ liệu từ WBS Master data của BMS sang hệ thống S/4 | New Function | F_4.03 | M |  | 1 |  |  | 0.65 |  |  | 0.65 | 4.5 |  |  | 4.5 | 0.83333 | [17 empty] | 1 | 1 |  |  | 1 |  |  |  | 1 | 1 | 1 | 1 |  | 5 | 6.6667 | 5
|  | 4.04 | Đồng bộ Budget Planning sang hệ thống S4 | Đẩy thông tin dữ liệu planning từ BMS sang hệ thống S/4 | New Function | F_4.04 | M |  | 1 |  |  | 0.65 |  |  | 0.65 | 5.7 |  |  | 5.7 | 1.0556 | [17 empty] | 1 | 1 |  |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 |  | 6.3333 | 8.4444 | 6.3333
|  | 4.05 | Đồng bộ WBS sang hệ thông Upstream | Đẩy thông tin dữ liệu từ WBS Master data của BMS sang Upstream, đồng thời đẩy Actual + Commitment từ Upstream sang BMS | New Function | F_4.05 | M |  | 1 |  |  | 0.65 |  |  | 0.65 | 4.7 |  |  | 4.7 | 0.87037 | [17 empty] | 1 | 1 |  |  | 1 |  |  |  | 3 | 1 | 1 | 1 |  | 5.2222 | 6.963 | 5.2222
|  | 4.06 | Đồng bộ actual Consumption từ S4 | Đẩy từ Consumption từ BMS sang S/4 | New Function | F_4.06 | M |  | 1 |  |  | 0.65 |  |  | 0.65 | 4.6 |  |  | 4.6 | 0.85185 | [17 empty] | 1 | 1 |  |  | 1 |  |  |  | 2 | 1 | 1 | 1 |  | 5.1111 | 6.8148 | 5.1111
|  | 4.07 | Đồng bộ dữ liệu budget commitment + actual từ hệ thống Upstream | Đẩy dữ liệu từ Upstream về BMS để biết được Consumption
Total Functions |  |  | 29 |  |  |  |  | 16 | 8 | 5 |  |  |  |  | 18.9 | 143.1 |  |  | 143.1 | 26.5 | [30 empty] | 129.5556 | 172.7407 | 129.5556
302.2963
[7 empty] | 4) Non-similarity is used to adjust Efforts (MM) in case that our function is reused some parts from other function. | [12 empty] | #REF! | [30 empty] | 2 | 6 | 6
[7 empty] | 5) Complexity is used to adjust FP in case that the calculated FP from standard seems too high or low. | [43 empty] | 3.2389 | 1.4395 | 1.0796
[51 empty] | 4 | 2 | 2
[5 empty] | Kaizen Function Type | Priority
[5 empty] | New Function | M
[5 empty] | Modified Function | P
[5 empty] | BCT Testing Function | C
No Action
Note on F7: ====== ID#AAAAQxE5fko Kaizen Function Type (2021-11-06 07:39:38) 1) New Function -- adding new function to the system. 2) Modified Function -- modify existing function in the system. 3) BCT Testing Function -- no change to the function, but needed to do BCT Testing.
Note on H7: ====== ID#AAAAQxE5fkc 浅香義明 (2021-11-06 07:39:38) M: Mandatory C: Cancel / Deleted

## Fixed cost catagory historical
Company Name : |  | TMV
Classification Fixed cost and variable cost |  |  |  |  | Due Date : 19 Jan 2023 | [23 empty] | Due Date : 27 Jan 2023 | [7 empty] | Due Date : 8 Feb 2023 | [15 empty] | Due Date : 19 Jan 2023 | [17 empty] | Due Date : 27 Jan 2023 | [8 empty] | Due Date : 8 Feb 2023
[53 empty] | FY23 2Q vs FY23 3Q | [7 empty] | Please fill the reason with amount | FY22 actual vs FY23 3Q | [7 empty] | Please fill the reason with amount | FY23 3Q vs FY24 1st Cut | [7 empty] | Please fill the reason with amount | FY24 1st Cut vs FY26 Feb'23 | [7 empty] | Please fill the reason with amount | FY24 1st Cut vs FY26 Feb'22 | [7 empty] | Please fill the reason with amount
| Variance analysis of P/L |  |  |  | FY23 2Q (a) | [7 empty] | FY23 3Q (b) | [7 empty] | FY22 Actual ( c) | [7 empty] | FY24 1st Cut (d) | [7 empty] | FY26 Feb 23 (e) | [7 empty] | FY26 Feb 22 (f) | [7 empty] | Gap | [7 empty] | Reason | Gap | [7 empty] | Reason | Gap | [7 empty] | Reason | Gap | [7 empty] | Reason | Gap | [7 empty] | Reason
[53 empty] | (f=b-a) | Converntional |  |  | New prioritize |  |  |  |  | (g=b-c) | Converntional |  |  | New prioritize |  |  |  |  | (g=b-c) | Converntional |  |  | New prioritize |  |  |  |  | (g=b-c) | Converntional |  |  | New prioritize |  |  |  |  | (g=b-c) | Converntional |  |  | New prioritize
[5 empty] | Total | Conventional |  |  | New prioritize |  |  |  | Total | Conventional |  |  | New prioritize |  |  |  | Total | Conventional |  |  | New prioritize |  |  |  | Total | Conventional |  |  | New prioritize |  |  |  | Total | Conventional |  |  | New prioritize |  |  |  | Total | Conventional |  |  | New prioritize |  |  |  | Mil. Local Cur | [8 empty] | Mil. Local Cur | [8 empty] | Mil. Local Cur | [8 empty] | Mil. Local Cur | [8 empty] | Mil. Local Cur
[6 empty] | Volume related | New Model (FMC/New introduction) | Ordinary expense | Value Chain & New Mobility | Carbon Neutral Strategy (CN) | Asia Digital Transformation (DX) | Others |  | Volume related | New Model (FMC/New introduction) | Ordinary expense | Value Chain & New Mobility | Carbon Neutral Strategy (CN) | Asia Digital Transformation (DX) | Others |  | Volume related | New Model (FMC/New introduction) | Ordinary expense | Value Chain & New Mobility | Carbon Neutral Strategy (CN) | Asia Digital Transformation (DX) | Others |  | Volume related | New Model (FMC/New introduction) | Ordinary expense | Value Chain & New Mobility | Carbon Neutral Strategy (CN) | Asia Digital Transformation (DX) | Others |  | Volume related | New Model (FMC/New introduction) | Ordinary expense | Value Chain & New Mobility | Carbon Neutral Strategy (CN) | Asia Digital Transformation (DX) | Others |  | Volume related | New Model (FMC/New introduction) | Ordinary expense | Value Chain & New Mobility | Carbon Neutral Strategy (CN) | Asia Digital Transformation (DX) | Others |  | Volume related | New Model (FMC/New introduction) | Ordinary Expense | Value Chain & New Mobility | Carbon Neutral Strategy (CN) | Asia Digital Transformation (DX) | Others |  |  | Volume related | New Model (FMC/New introduction) | Ordinary Expense | Value Chain & New Mobility | Carbon Neutral Strategy (CN) | Asia Digital Transformation (DX) | Others |  |  | Volume related | New Model (FMC/New introduction) | Ordinary Expense | Value Chain & New Mobility | Carbon Neutral Strategy (CN) | Asia Digital Transformation (DX) | Others |  |  | Volume related | New Model (FMC/New introduction) | Ordinary Expense | Value Chain & New Mobility | Carbon Neutral Strategy (CN) | Asia Digital Transformation (DX) | Others |  |  | Volume related | New Model (FMC/New introduction) | Ordinary Expense | Value Chain & New Mobility | Carbon Neutral Strategy (CN) | Asia Digital Transformation (DX) | Others
| Labor cost | Plant Labor Cost |  | Variable | 8.7851 | 9.824 |  | -1.0389 |  |  |  |  | 0 | [7 empty] | 7.9382 | 9.2855 |  | -1.3473 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | -8.7851 | -9.824 | 0 | 1.0389 | 0 | 0 | 0 | 0 |  | -7.9382 | -9.2855 | 0 | 1.3473 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Plant Labor Cost |  | Fixed | 2.7542 |  |  | 2.7542 |  |  |  |  | 0 | [7 empty] | 3.0558 |  |  | 3.0558 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | -2.7542 | 0 | 0 | -2.7542 | 0 | 0 | 0 | 0 |  | -3.0558 | 0 | 0 | -3.0558 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Labor Cost (SGA) |  | Fixed | 18.4033 |  |  | 18.4033 |  |  |  |  | 0 | [7 empty] | 16.8245 |  |  | 16.8245 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | -18.4033 | 0 | 0 | -18.4033 | 0 | 0 | 0 | 0 |  | -16.8245 | 0 | 0 | -16.8245 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 29.9426 | 9.824 | 0 | 20.1186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.8185 | 9.2855 | 0 | 18.533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -29.9426 | -9.824 | 0 | -20.1186 | 0 | 0 | 0 | 0 |  | -27.8185 | -9.2855 | 0 | -18.533 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Welfare expenses |  |  | Fixed | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Existing Project |  |  | 14.1151 | 0 | 2.3909 | 11.7242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6201 | 0 | 0 | 13.6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14.1151 | 0 | -2.3909 | -11.7242 | 0 | 0 | 0 | 0 |  | -13.6201 | 0 | 0 | -13.6201 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Depreciation | Manu |  | Fixed | 9.7918 | 0 | 1.896 | 7.8958 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 9.7622 | 0 | 0 | 9.7622 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | -9.7918 | 0 | -1.896 | -7.8958 | 0 | 0 | 0 | 0 |  | -9.7622 | 0 | 0 | -9.7622 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PJT Investment (Cat. 1 & 2 ) | Fixed | [66 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Production related (Cat. 4) | Fixed | [66 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Supplier tooling (Cat. 3) | Variable: TMT Fixed: Another country | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | IT Expenses (Cat. 5) |  | Fixed | 0.82796 | 0 | 0 | 0.82796 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0.63 | 0 | 0 | 0.63 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | -0.82796 | 0 | 0 | -0.82796 | 0 | 0 | 0 | 0 |  | -0.63 | 0 | 0 | -0.63 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | SGA (Cat. 5) |  | Fixed | [66 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Others (SGA depre) (Cat. 6/7) |  | Fixed | 3.4953 | 0 | 0.49485 | 3.0005 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 3.2279 | 0 | 0 | 3.2279 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | -3.4953 | 0 | -0.49485 | -3.0005 | 0 | 0 | 0 | 0 |  | -3.2279 | 0 | 0 | -3.2279 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New Investment/Project (Link with CAPEX/PP06) |  |  | 0.8758 | 0 | 0.20299 | 0.67282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.8758 | 0 | -0.20299 | -0.67282 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Manu |  | Fixed | 0.54766 | 0 | 0.20299 | 0.34467 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | -0.54766 | 0 | -0.20299 | -0.34467 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PJT Investment (Cat. 1 & 2 ) | Fixed | [66 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Production related (Cat. 4) | Fixed | [66 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Supplier tooling (Cat. 3) | Variable: TMT Fixed: Another country | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | IT Expenses (Cat. 5) |  | Fixed | 0.27823 | 0 | 0 | 0.27823 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | -0.27823 | 0 | 0 | -0.27823 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | SGA (Cat. 5) |  | Fixed | [66 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Others (SGA depre) (Cat. 6/7) |  | Fixed | 0.049918 | 0 | 0 | 0.049918 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | -0.049918 | 0 | 0 | -0.049918 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 14.9909 | 0 | 2.5939 | 12.397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6201 | 0 | 0 | 13.6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14.9909 | 0 | -2.5939 | -12.397 | 0 | 0 | 0 | 0 |  | -13.6201 | 0 | 0 | -13.6201 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| R&D cost |  |  | Fixed | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Warranty expenses |  |  | Fixed | 2.8453 |  |  | 2.8453 |  |  |  |  | 0 | [7 empty] | 2.4446 | 0 | 0 | 2.4446 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | -2.8453 | 0 | 0 | -2.8453 | 0 | 0 | 0 | 0 |  | -2.4446 | 0 | 0 | -2.4446 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| General expenses | Plant Repair & Maintenance |  | Fixed | 1.7116 |  |  | 1.7116 |  |  |  |  | 0 | [7 empty] | 1.6321 | 0 | 0 | 1.6321 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | -1.7116 | 0 | 0 | -1.7116 | 0 | 0 | 0 | 0 |  | -1.6321 | 0 | 0 | -1.6321 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Plant General Expenses (COM-Electric, Water & Gas Expenses) |  | Variable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IH Mfg cost ( Operating Supply, Cosumable Tools, Milkrun) | Variable | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Freight | Variable | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Utility (elctricity, fuel, gas, water) | Variable | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Plant General Expenses |  | Fixed | 7.137 |  | 5.6121 | 1.525 |  |  |  |  | 0 | [7 empty] | 4.4375 | 0 | 2.63 | 1.8075 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | -7.137 | 0 | -5.6121 | -1.525 | 0 | 0 | 0 | 0 |  | -4.4375 | 0 | -2.63 | -1.8075 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | IT Expenses |  | Fixed | 1.1008 |  |  | 0.84781 |  |  | 0.253 |  | 0 | [7 empty] | 0.82127 | 0 | 0 | 0.82127 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | -1.1008 | 0 | 0 | -0.84781 | 0 | 0 | -0.253 | 0 |  | -0.82127 | 0 | 0 | -0.82127 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | General Expense (SGA) |  | Fixed | 9.4685 |  |  | 9.3965 | 0.072012 |  |  |  | 0 | [7 empty] | 6.9939 | 0 | 0 | 6.9939 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | -9.4685 | 0 | 0 | -9.3965 | -0.072012 | 0 | 0 | 0 |  | -6.9939 | 0 | 0 | -6.9939 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bad debt (Provision of Doubtful Debts) |  | Fixed | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 19.4179 | 0 | 5.6121 | 13.4809 | 0.072012 | 0 | 0.253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.8848 | 0 | 2.63 | 11.2548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19.4179 | 0 | -5.6121 | -13.4809 | -0.072012 | 0 | -0.253 | 0 |  | -13.8848 | 0 | -2.63 | -11.2548 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Selling cost |  |  | Fixed | 12.7898 |  | 2.2701 | 9.548 | 0.27176 |  |  | 0.7 | 0 | [7 empty] | 7.1137 | 0 | 3.49 | 3.6237 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [7 empty] | 0 | [7 empty] | -12.7898 | 0 | -2.2701 | -9.548 | -0.27176 | 0 | 0 | -0.7 |  | -7.1137 | 0 | -3.49 | -3.6237 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 79.9866 | 9.824 | 10.4761 | 58.3898 | 0.34377 | 0 | 0.253 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64.8818 | 9.2855 | 6.12 | 49.4763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -79.9866 | -9.824 | -10.4761 | -58.3898 | -0.34377 | 0 | -0.253 | -0.7 |  | -64.8818 | -9.2855 | -6.12 | -49.4763 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total FC | [54 empty] | Check | 0 | should be 0 | [6 empty] | Check | 0 | should be 0 | [6 empty] | Check | 0 | should be 0 | [6 empty] | Check | 0 | should be 0 | [6 empty] | Check | 0 | should be 0
CAPEX Investment & depre
| Investment (Should tie up with CAPEX/PP06 Submission | 1. PE & Production preparation
2. Mfg Preparation
3. Supplier Tooling
4. Production Related
5. SGA & IT DX
6. Carbon Neutral
Total
| B. Depreciation (inform depre reflected on above FC template) | 1. PE & Production preparation
| 1. PE & Production preparation | 2. Mfg Preparation
| 2. Mfg Preparation | 3. Supplier Tooling
| 3. Supplier Tooling | 4. Production Related
| 4. Production Related | 5. SGA & IT DX
| 5. SGA & IT DX | 6. Carbon Neutral
| 6. Carbon Neutral | Total
Please ensure total fixed cost is same figure with OI & Profit by segment
Attachment M
NOTE for CAPEX:
1. Please ensure CAPEX linkage with CAPEX submission on 13 Jan'23 for MTP and 17 Jan'23 PP06 Conets for FY24
2. Please ensure that investment is linkage with "Depre New Project/Investment" in the above FC template
NOTE for Existing Depre MANU: If company unable to breakdown as template, company can combine PJT Investment and Production Related.

## Sheet1 (hidden)
Triển khai theo phương pháp Agile
ID | Giai đoạn |  | Tháng | Tuần | Nhân sự
S1 | Sprint 1 | Master data PR Bidding, Collect quotation user request (Catalog) PO (Catalog và vendor portal) GR (Bao gồm mobi-app) Invoice (nhập thủ công) Đề nghị thanh toán Báo cáo danh sách Phê duyệt (bao gồm mobi-app) | 9.25 | 37
S1.1 | User requirement | Chia sẻ quy trình Giới thiệu mock-up tính năng Thu thập yêu cầu bổ sung (GAP) Phân tích bổ sung yêu cầu --> đưa vào CR (nếu có) | 0.25 | 1
S1.2 | Development | DEV và test Tài liệu User manual | 4 | 16
S1.3 | System test | bao gồm cả test full luồng | 1 | 4
S1.4 | UAT | Xây dựng tài liệu UAT Training UAT | 1 | 4
S1.5 | Trial | Chạy thử | 2 | 8
S1.6 | Deploy, golive and support | Chuẩn bị hệ thống Chuyển code chuyển đổi data | 1 | 4
S2 | Sprint 2 | Sourcing Báo cáo dashboard: - mua hàng - Tiến độ giao hàng Invoice: - Tích hợp email để lấy thông tin hóa đơn điện tử về Tích hợp email để gửi thông báo về email contract: - Tạo Contract - Quản lý contract template - Tích hợp in Contract pdf - Copy thông tin thành bảng giá Đánh giá NCC định kỳ, báo cáo dashboard mobi-app | 6.25 | 25
S2.1 | User requirement | Chia sẻ quy trình Giới thiệu mock-up tính năng Thu thập yêu cầu bổ sung (GAP) Phân tích bổ sung yêu cầu --> đưa vào CR (nếu có) | 0.25 | 1
S2.2 | Development | DEV và test Tài liệu User manual | 2 | 8
S2.3 | System test | bao gồm cả test full luồng | 1 | 4
S2.4 | UAT | Xây dựng tài liệu UAT Training UAT | 1 | 4
S2.5 | Trial | Chạy thử | 1 | 4
S2.6 | Deploy, golive and support | Chuẩn bị hệ thống Chuyển code chuyển đổi data | 1 | 4
|  |  | 15.5 | 62

## FP Guideline (hidden)
Phase | [13 empty] | Project Name | [5 empty] | TMAP Standard | [45 empty] | Page
Block Name | [13 empty] | TMAP Management Standard | [15 empty] | Function Name | [7 empty] | 1. Management Guideline | [22 empty] | Created | 2006-03-01 |  |  | By |  | FSBT) Suzuki
Document Name | [31 empty] | Title | [5 empty] | 1.3 Estimation | [22 empty] | Updated | 2009-02-12 |  |  | By |  | Anan
Estimation Guideline
Objectives
| - | Make development efforts estimation more concrete and rational.
Overview
| - | Function Point Analysis (F.P.) is used in the development efforts estimation for DR-ST.
| - | F.P. is a mean to determine the degree of difficulty to develop a system. The requirements of a system will be collected and broken down into the level of system function,
i.e. screen, batch and report. Then, the components of function, e.g. the number of updated/retrieved logical tables, will be analyzed and determined for F.P. of the function.
The analysis of requirements to determine F.P. follows information described in Section "3. Standard for F.P." below.
| - | After F.P. of each function is determined, the development efforts of the function will be estimated by dividing F.P with Productivity of the vendor. Please refer to Section "2. Productivity" for details.
1. Procedure on determining Software Size Estimation of F.P.
In order to estimate development efforts, F.P. will be determined by the following procedure in UR phase.
| 1.1 |  | Requirements Collection
User requirements are collected and broken down into the level of system function, i.e. screen, batch and report.
High-level design of each function is determined and confirmed, e.g. rough layout of screen, update/retrieve logical table.
| 1.2 |  | Function Analysis and F.P. Calculation
Based on table in Section 3 below, a function will be analyzed in terms of components and tasks, e.g. the number of logical
tables to be updated or retrieved. Then, the analyzed information will be filled in Function List for the F.P. calculation of the function.
| 1.3 |  | Development Efforts Calculation
Development efforts for each function will be calculated as the following formula.
[6 empty] | Development efforts for a certain function | [15 empty] | = |  |  |  |  | F.P. of a certain function
Vendor productivity to finish that type of function
2. Productivity
Productivity is defined to be how much F.P. of a certain function we can develop in one month. Productivity is separated into Screen, Batch and Report productivities.
2.1 Standard Productivity
TMC has provided the following standard productivity for determining standard development efforts. All vendors are required to have productivity at least the standard productivity.
[5 empty] | Screen |  |  |  |  | 4.2 F.P./1 MM | [9 empty] | Example :
[5 empty] | Report |  |  |  |  | 4.6 F.P./1MM | [10 empty] | Efforts of 2.0 F.P. of screen is 2.0/4.2 = 0.48 MM
[5 empty] | Batch |  |  |  |  | 4.6 F.P./1MM
2.2 Vendor Productivity
In case that productivity of a vendor is greater than or equal to standard productivity, the actual productivity of that vendor will be used. However, if the vendor productivity is
less than standard productivity, the standard productivity will be used. All vendors are required to improve their productivity to be greater than or equal to the standard productivity.
3. Standard for F.P.
Before counting FP, the system is broken down to system function level, i.e. screen, batch and report. The estimation is carried on functions and
adjust the commonized part by using non-similarity ratio -- if we commonize functions for 20%, that means non-similarity ratio is 80% or 0.8.
The same concept is also applied for common function such as common receiving batch, non-similarity ratio is used to adjust the efforts by using
this common function. TMAP standard provides some common function, e.g. common receiving batch.
| * | Unit column will be used to fill in Function List for calculate FP for the corresponding function.
The Standard of F.P. for each function is defined as follows.
| Function | [25 empty] | F.P. |  | Unit* | [6 empty] | Calculation | [15 empty] | Description
| Screen |  | Master/Transaction |  | Basic for retrieve | [21 empty] | 1 |  | 1 | [6 empty] | Always 1 if retrieving exists (basic for 1 target table) | [15 empty] | Retrieve data from table and show on screen. Table here is logical table. Please see definition of logical table below. Retrieve here is including Search and View.
[5 empty] | Basic for update | [21 empty] | 1 |  | 1 | [6 empty] | Always 1 if updating exists (basic for 1 target table) | [15 empty] | Get data from screen and update data to a table. Table here is logical table. Please see definition of logical table below. Update here means already included Add, Delete, Edit modes.
[5 empty] | Increase target tables of retrieve | [21 empty] | 0.2 |  | # of table | [6 empty] | # of table * 0.2 (# of table here excluding 1 that is already considered in basic for retrieve) | [15 empty] | Increase number of target tables for retrieving. Table here is logical table. Please see definition of logical table below. Retrieve here is including Search and View.
[5 empty] | Increase target tables of update | [21 empty] | 0.3 |  | # of table | [6 empty] | # of table * 0.3 (# of table here excluding 1 that is already considered in basic for updating) | [15 empty] | Increase number of target tables for updating. Table here is logical table. Please see definition of logical table below. Update here means already included Add, Delete, Edit modes.
[5 empty] | Set combobox accessing table （fetch table） | [21 empty] | 0.1 |  | # of combobox | [6 empty] | # of combobox * 0.1 | [15 empty] | Number of combobox that need to access table for showing data list in the combobox. One combobox will access one table, and the task of access table is already included here, not count in "increase target tables of retrieve". Table here is logical table.
[5 empty] | Display sub-screen | [21 empty] | 0.5 |  | # of sub-screen | [6 empty] | # of sub-screen * 0.5 | [15 empty] | e.g. data-showing or maintenance subscreens, not include error message showing subscreen. Edit or View mode of the same sub-screen is considered to be only one sub-screen.
[5 empty] | Refer and check with master | [21 empty] | 0.1 |  | # of table | [6 empty] | # of table * 0.1 | [15 empty] | Refer to Master and perform business validation => # of table to be refered is put in here, and not include with "Basic for retrieve" and "Increase target tables of retrieve"
[5 empty] | Check input items | [21 empty] | 0.1 |  | # of item | [6 empty] | (# of item / 5 items) * 0.1 | [15 empty] | Perform format validation with the client's input data. This also includes checking of mandatory field.
[5 empty] | Additional functions・On Screen | [21 empty] | 0.5 |  | # of function | [6 empty] | # of function * 0.5 | [15 empty] | Additional functions, e.g. calculation, that perform on client, and no access to server.
[5 empty] | Additional functions・Need to access server | [21 empty] | 1 |  | # of function | [6 empty] | # of function * 1.0 | [15 empty] | Additional functions that needs to access server, or execute on server. This does not include View, New, Edit and Delete which are already considered in Basic for retrieve and update.
|  |  | On-Demand Batch |  | Basic | [21 empty] | 1 |  | 1 | [6 empty] | 1 on-demand batch | [15 empty] | On-demand batch related on-screen and job invoking tasks, e.g. select upload file, invoke job, display the results. This does not include batch application. The batch application's FP calculation will be put in Batch Section, e.g. upload, calculation/data
[5 empty] | Additional functions | [21 empty] | 0.5 |  | # of function | [6 empty] | # of function * 0.5 | [15 empty] | Additional functions of the on-demand batch that performs on client, and no access to server.
| Report |  | Report |  | Basic | [21 empty] | 1 |  | 1 | [6 empty] | Always 1 (Basic for 1 target table&1 form) | [15 empty] | Showing data from a target table to a form of report => layout is simple layout in which data will be shown in row by row. Table here is logical table. Please see definition of logical table below.
[5 empty] | Increase target tables | [21 empty] | 0.2 |  | # of table | [6 empty] | # of table * 0.2 (# of table here excluding 1 that is already considered in basic for report) | [15 empty] | Total number of increase target tables to show on report (can be many forms). Table here is logical table. Please see definition of logical table below.
[5 empty] | Increase forms | [21 empty] | 1 |  | # of form | [6 empty] | # of form * 1.0 (# of form here excluding 1 that is already considered in basic for report) | [15 empty] | number of increase forms of report
[5 empty] | Special edit | [21 empty] | 0.1 |  | # of edited field | [6 empty] | (# of edited field / 3) * 0.1 | [15 empty] | Doing edit/calculation on a field before showing on report
[5 empty] | Special Layout | [21 empty] | 0.5 |  | # of area | [6 empty] | # of area * 0.5 | [15 empty] | Layout is not row by row layout, e.g. graph, summary data. For example, if # of graphs is 3, # of area will be 3.
| Batch |  | Upload |  | Basic（file read, data format check, store to table） | [21 empty] | 1 |  | 1 | [6 empty] | Always 1 (Basic for uploading data to 1 target table) | [15 empty] | Doing basic tasks of file upload, e.g. file read, data format check, and update to a target table. Table here is logical table. Please see definition of logical table below.
[5 empty] | Increase target tables | [21 empty] | 0.3 |  | # of table | [6 empty] | # of table * 0.3 (# of table here excluding 1 that is already considered in basic for uploading) | [15 empty] | the number of increase target tables for updating file upload info. Table here is logical table. Please see definition of logical table below.
[5 empty] | Refer and check master | [21 empty] | 0.1 |  | # of table | [6 empty] | # of table * 0.1 | [15 empty] | Refer to Master and perform business validation => # of table to be refered is put in here, and not include with "Basic" and "Increase target tables". Table here is logical table. Please see definition of logical table below.
[5 empty] | Data convert and edit | [21 empty] | 0.1 |  | # of item | [6 empty] | (# of item / 3) * 0.1 | [15 empty] | Converting/calculating file data before store into table
[5 empty] | Communicate with other system | [21 empty] | 1 |  | 1 | [6 empty] | Always 1 | [15 empty] | This is the case that the uploaded file is transferred from other system. (Then this file will be uploaded later into our system). If using TMAP Standard Framework for file transferring, this item will not be counted.
[5 empty] | Additional function | [21 empty] | 1 |  | # of function | [6 empty] | # of function * 1.0 | [15 empty] | Additional functions apart from the mentioned one
|  |  | Download (Export) |  | Basic（fetch table, create file） | [21 empty] | 1 |  | 1 | [6 empty] | Always 1 (Basic for fetching data from 1 target table) | [15 empty] | Fetch data from a table, and create the downloaded file. Table here is logical table. Please see definition of logical table below.
[5 empty] | Increase target tables | [21 empty] | 0.2 |  | # of table | [6 empty] | # of table * 0.2 (# of table here excluding 1 that is already considered in basic for downloading) | [15 empty] | Increase number of tables to be fetched data. Table here is logical table. Please see definition of logical table below.
[5 empty] | Refer and check master | [21 empty] | 0.1 |  | # of table | [6 empty] | # of table * 0.1 | [15 empty] | Refer to Master and perform business validation => # of table to be refered is put in here, and not include with "Basic" and "Increase target tables". Table here is logical table. Please see definition of logical table below.
[5 empty] | Data convert and edit | [21 empty] | 0.1 |  | # of item | [6 empty] | (# of item / 3) * 0.1 | [15 empty] | Converting/calculating data from table before creating the file.
[5 empty] | Communicate with other system | [21 empty] | 1 |  | 1 | [6 empty] | Always 1 | [15 empty] | This is the case that the file is transferred to other system. If using TMAP Standard Framework for file transferring, this item will not be counted.
[5 empty] | Additional function | [21 empty] | 1 |  | # of function | [6 empty] | # of function * 1.0 | [15 empty] | Additional functions apart from the mentioned one
|  |  | Calculation/Data Edit |  | Calculation, Data Edit | [21 empty] | 1 |  | # of function | [6 empty] | # of function * 1.0 | [15 empty] | Process/function to calculate/edit data
[Logical Table]
The way to count # of table: Count Logical table -- table that consists of a header table and several detail tables => in this case the number of
table is counted as 1.
For example, in case of issuing PO that have delivery dates at most 2 days (times). There are at least two possible ways to design as below.
But there is only one logical table for estimating in this case -- PO logical table.
[Example]
Assumed example of "Supplier Master Maintenance" screen, which has operation flow shown as follows :
|  | Re-Invoicing System | [20 empty] | Manual Operation
Remarks :
[38 empty] | 1) |  | Supplier Master Inquiry Screen is a main screen to search and show supplier
information on screen. See image below.
[38 empty] | 2) |  | Supplier Master Detail Screen is a sub-screen to view details or edit supplier
information. See image below.
[38 empty] | 3) |  | Supplier information are retrieved from and updated to Supplier Master and Supplier Plant
Master tables.
[38 empty] | 4) |  | Assumed that there is no business validation and format validation.
Supplier Master Detail Screen
Supplier Information
Supplier Master Inquiry Screen
[52 empty] | Supplier Code: | XXXX | [9 empty] | Supplier Name:
[12 empty] | Supplier Code: | xxxx |  |  |  | - | x |  |  |  |  | Supplier Name: | x(30) | [27 empty] | Payment Term: | [10 empty] | Credit Term: | days
[12 empty] | Max Record: | 999 | [17 empty] | Search | [20 empty] | Oracle Code: | [10 empty] | System Supplier:
Payment Plant:
|  |  |  | Add | [5 empty] | Edit | [5 empty] | Delete |  |  |  | View
|  |  |  | Supplier List | [39 empty] | Supplier Plant Information
[7 empty] | No |  | Supp Code | [5 empty] | Supplier Name
[8 empty] | 1 | DITH-C | [5 empty] | Denso | [36 empty] | Supplier: | XXXX-X | [9 empty] | Plant Name:
[8 empty] | 2 | ATCI-A | [5 empty] | Vutec
[52 empty] | Oracle Code: | [10 empty] | VAT rate: | %
[52 empty] | WHT Type: | [10 empty] | WHT Rate: | %
[26 empty] | First |  |  | Prev |  |  |  | Next |  |  |  | Last
[44 empty] | Save | [5 empty] | Close
[14 empty] | Productivity |  |  |  |  | 1.1 |  | 2.2 | 3.3
|  | Function | [16 empty] | Screen |  | Batch | Report |  | FunctionPoint | [5 empty] | Screen | [11 empty] | Report |  |  |  |  | Batch
[30 empty] | Mater/Transaction | [9 empty] | ODB |  | Report |  |  |  |  | Upload | [5 empty] | Download | [5 empty] | Calculation/Data Edit
[24 empty] | FP | Non-Similarity |  | Complexity | MM |  | Basic for Retreive (always 1) | Basic for Update (always 1) | Increase Target Tables (retrieve) | Increase Target Tables (update) | Combobox accessing Table | Display Sub-Screen | Refer/Check Master | Check Input Items | Additional Functions (on Screen) | Additional Functions (Server Access) | Basic | Additional Functions | Basic | Increase Target Tables | Increase Forms | Special Edit | Special Layout | Basic | Increase target tables | Refer/Check Master | Data convert and edit | Communicate with other system | Additional function | Basic | Increase target tables | Refer/Check Master | Data convert and edit | Communicate with other system | Additional function
|  | Supplier Master Maintenance | [16 empty] | 1 |  |  |  |  | 3.2 |  |  |  | 2.9091 |  | 1 | 1 | 1 | 1 | 2 | 1
|  | Note : |  |  |  | - Non-similarity is used to adjust efforts in case that our function is reused some parts from other function. For example, if Func-B reuses
some parts of Func-A for 20%, it means non-similarity will be 1.0-0.2 = 0.8. The value of Non-similarity is from 0 to 1.
- Complexity is used to adjust FP in case that the calculated FP from standard seems too high or low. If it is too high, we can
adjust by using complexity, for example if we think it should be 10% lower than standard, the complexity will be 0.9. And if it is too low
and we think it should be 10% higher than standard, the complexity will be 1.1. The value of complexity is greater or equal to 0.
PO No
Date
Header
PO No
Part No
Price
Discount
Detail : Basic Info
PO No
Part No
Delivery Date
Quantity
Detail : Delivery Info
PO Logical Table -- Pattern 1
PO No
Date
Header
PO No
Part No
Delivery Date 1
Quantity 1
Delivery Date 2
Quantity 2
Price
Discount
Detail : Basic Info
PO Logical Table -- Pattern 2
Count as one logical table when estimate for function point
Supplier Master Inquiry Screen
Supplier Master
Maintenance
Supplier Master
Supplier Master Detail Screen
Supplier Plant Master